## RAID DASHBOARD
RAID LOG & DASHBOARD
Programme Name: |  |  | Programme Health |  |  |  | 0-30= Excellent governance health
Project Manager: |  |  | Green |  |  |  | 31-60 = Needs attention
|  |  | Governance Health Score: |  | 0 |  | 61+ = Significant concern
Risks |  | Assumptions |  |  |  | Issues |  |  | Dependencies
0
0
Green
0 |  | 0 |  |  |  | 0 |  |  | 0
LEVEL
| High |  |  | High |  |  |  | High |  | High
Moderate
| Low |  |  | Moderate |  |  |  | Moderate |  | Moderate
| TREND |  |  | Low |  |  |  | Low |  | Low
Deteriorating
No Change
Improving
| Mitigated |  |  | Upheld |  |  |  | Closed |  | Committed
Date |  | Version |  |  |  | Overall Status |  |  | Stakeholders
V1.0
Executive Summary

## Risks
RISKS
Fill in Grey fields ONLY | [12 empty] | RAID SUMMARY
(PROJECT NAME) |  |  |  | Number of Risks | [8 empty] | RISKS
|  |  |  | High | [8 empty] | ASSUMPTIONS
|  |  |  | Moderate | [8 empty] | ISSUES
|  |  |  | Low | [8 empty] | DEPENDENCIES
|  | Mitigated |  | Total | 0
RISK ID | TITLE | DESCRIPTION | IMPACT | DATE ADDED | RISK |  |  |  | STATUS | MITIGATED | ACTIONS | LAST UPDATED | TREND | OWNER | DATE DUE
|  |  |  | DD/MM/YY | IMPACT | LIKELIHOOD | SCORE | LEVEL
R001 |  | There is a risk that …
R002 |  | There is a risk that …
R003 |  | There is a risk that …
R004 |  | There is a risk that …
R005 |  | There is a risk that …
R006 |  | There is a risk that …
R007 |  | There is a risk that …
R008 |  | There is a risk that …
R009 |  | There is a risk that …
R010 |  | There is a risk that …
R011 |  | There is a risk that …
R012 |  | There is a risk that …
R013 |  | There is a risk that …
R014 |  | There is a risk that …
R015 |  | There is a risk that …
R016 |  | There is a risk that …
R017 |  | There is a risk that …

## Assumptions
ASSUMPTIONS
Fill in Grey fields ONLY
(PROJECT NAME) | [5 empty] | Number of Assumptions |  |  |  | RAID SUMMARY
[6 empty] | High |  |  |  | RISKS
[6 empty] | Moderate |  |  |  | ASSUMPTIONS
|  | Upheld |  |  |  | Low |  |  |  | ISSUES
[6 empty] | Total | 0 |  |  | DEPENDENCIES
RISK ID | TITLE | DESCRIPTION | IMPLICATION | DATE ADDED | ASSUMPTION/CONSTRAINT | RECORDED BY | STAKEHOLDERS INVOLVED | CRITICALITY | STATUS | ACTIONS | LAST UPDATED | OWNER | NOTES
A001 |  | There is an assumption that …
A002 |  | There is an assumption that …
A003 |  | There is an assumption that …
A004 |  | There is an assumption that …
A005 |  | There is an assumption that …
A006 |  | There is an assumption that …
A007 |  | There is an assumption that …
A008 |  | There is an assumption that …
A009 |  | There is an assumption that …
A010 |  | There is an assumption that …
A011 |  | There is an assumption that …
A012 |  | There is an assumption that …
A013 |  | There is an assumption that …
A014 |  | There is an assumption that …
A015 |  | There is an assumption that …
A016 |  | There is an assumption that …
A017 |  | There is an assumption that …

## Issues
ISSUES
Fill in Grey fields ONLY
(PROJECT NAME) |  |  | Number of Issues |  |  |  |  | RAID SUMMARY
|  |  | High |  |  |  |  | RISKS
|  |  | Moderate |  |  |  |  | ASSUMPTIONS
| Closed |  | Low |  |  |  |  | ISSUES
|  |  | Total | 0 |  |  |  | DEPENDENCIES
RISK ID | TITLE | DESCRIPTION | IMPACT DESCRIPTION | DATE ADDED | ISSUE SCORE | STATUS | ACTIONS | LAST UPDATED | OWNER | DATE DUE
I001
I002
I003
I004
I005
I006
I007
I008
I009
I010
I011
I012
I013
I014
I015
I016
I017

## Dependencies
DEPENDENCIES
Fill in Grey fields ONLY
(PROJECT NAME) |  |  | Number of Dependencies |  |  |  |  | RAID SUMMARY
|  |  | High |  |  |  |  | RISKS
|  |  | Moderate |  |  |  |  | ASSUMPTIONS
| COMMITTED |  | Low |  |  |  |  | ISSUES | 0
|  |  | Total | 0 |  |  |  | DEPENDENCIES | 0
RISK ID | TITLE | DESCRIPTION | IMPACT DESCRIPTION | DATE ADDED | PRIORITY | STATUS | ACTIONS | LAST UPDATED | OWNER | DATE DUE
I001 |  | There is a dependency on …
I002 |  | There is a dependency on …
I003 |  | There is a dependency on …
I004 |  | There is a dependency on …
I005 |  | There is a dependency on …
I006 |  | There is a dependency on …
I007 |  | There is a dependency on …
I008 |  | There is a dependency on …
I009 |  | There is a dependency on …
I010 |  | There is a dependency on …
I011 |  | There is a dependency on …
I012 |  | There is a dependency on …
I013 |  | There is a dependency on …
I014 |  | There is a dependency on …
I015 |  | There is a dependency on …
I016 |  | There is a dependency on …
I017 |  | There is a dependency on …

## Risk Scoring
Key
| 1-4 | Low Risk
| 5-12 | Moderate Risk
| 13-25 | High Risk
Overview of Risk Score Matrix Based on Impact and Likelihood
The Risk Score Matrix tool is used to assess and prioritise risks by evaluating the impact and likelihood of potential events.
Each risk is rated on two dimensions:
Impact (the severity of consequences if the event occurs) and Likelihood (the probability of the event occurring). Both dimensions are scored on a scale of 1 to 5 and categorised into Low, Moderate, and High.
Components:
1. Impact:
- Low (1-2): The event will have minimal consequences.
- Moderate (3-4): The event will have noticeable but manageable consequences.
- High (5): The event will have severe consequences.
2. Likelihood:
- Low (1-2): The event is unlikely to occur.
- Moderate (3-4): The event has a reasonable chance of occurring.
- High (5): The event is highly likely to occur.
Matrix Structure:
Columns: Represent the Impact scores (1 to 5).
Rows: Represent the Likelihood scores (1 to 5).
Calculating the Risk Score:
The risk score is calculated by multiplying the Likelihood score by the Impact score. The result is then used to categorise the overall risk level.
Risk Categories:
Low Risk:
- Typically, a risk score between 1 and 4.
- Indicates low priority risks with minor consequences and low likelihood of occurrence.
Moderate Risk:
- Typically, a risk score between 5 and 12.
- Indicates medium priority risks with moderate consequences and/or moderate likelihood of occurrence.
High Risk:
- Typically, a risk score between 13 and 25.
- Indicates high priority risks with severe consequences and/or high likelihood of occurrence.
Example:
Impact Score: 3 (Moderate)
Likelihood Score: 4 (Moderate)
Risk Score: 3 X 4 = 12 (Moderate Risk)
The matrix helps in identifying and prioritising risks, enabling the team to focus on managing the most significant risks effectively. It provides a visual representation of risks, facilitating better decision-making and resource allocation.

## Help Page
The RAID log is used to document and track four critical aspects of our project: Risks, Assumptions, Issues, and Dependencies. Each component of the RAID log serves a specific purpose:
Risks: Potential problems that might occur in the future and have an impact on the project.
Assumptions: Things assumed to be true for the project to be successful.
Issues: Current problems that need to be resolved.
Dependencies: Tasks or activities that depend on the completion of other tasks or activities.
Risk Log
The Risk log is used to identify, assess, and manage risks that could impact the project. Risks are potential future events or conditions that, if they occur, can have a negative impact on the project's objectives, timeline, budget, or scope.
Key components of a Risk log include:
Risk ID: A unique identifier for each risk.
Title: A brief, descriptive title for the risk.
Description: A detailed description of the risk.
Impact: The potential impact of the risk on the project (e.g., high, moderate, low).
Likelihood: The probability of the risk occurring (e.g., high, moderate, low).
Owner: The person responsible for managing the risk.
Mitigation Plan: Actions planned to reduce the likelihood or impact of the risk.
Status: Indicates whether the risk is open or closed.
Mitigated: Indicates whether the risk has been mitigated (Yes/No).
Status: Open vs. Closed
Open:
Meaning: A risk is considered "open" if it is still a potential threat to the project. It has been identified and documented but has not yet occurred, or its impact is still being managed.
Example: The risk of a key supplier failing to deliver on time remains open until the delivery is confirmed.
Closed:
Meaning: A risk is marked as "closed" when it is no longer a threat to the project. This could be because the risk has been fully mitigated, the event has passed without occurring, or the project circumstances have changed, rendering the risk irrelevant.
Example: If the key supplier delivers on time, the risk of late delivery is closed.
Mitigated: Yes/No
Yes:
Meaning: If a risk is marked as "Yes" in the mitigated column, it means that effective actions have been taken to reduce the likelihood or impact of the risk.
Example: Implementing a backup supplier agreement to ensure materials are delivered on time even if the primary supplier fails.
No:
Meaning: If a risk is marked as "No" in the mitigated column, it means that no effective mitigation actions have been taken or that the planned actions have not yet been implemented.
Example: Knowing a supplier might delay delivery but not having any contingency plan in place.
Combining Status and Mitigation Columns
The combination of the status (open/closed) and the mitigated (Yes/No) columns provides a clear picture of the current state of each risk:
Open / No: The risk is still a potential threat, and no effective mitigation actions have been taken.
Open / Yes: The risk is still a potential threat, but actions have been taken to mitigate its impact or likelihood.
Closed / No: The risk is no longer a threat, but it was not mitigated (perhaps it resolved itself or became irrelevant).
Closed / Yes: The risk is no longer a threat because mitigation actions were effective.
By maintaining a comprehensive Risk log, we can proactively manage potential threats, ensuring that risks are identified, assessed, and mitigated to minimise their impact on the project.
Assumption Log
The Assumption log is a part of the RAID log specifically dedicated to tracking assumptions made during the project planning and execution phases. Assumptions are things that are accepted as true or certain to happen without proof.
They are necessary to proceed with planning, especially when there are unknowns or uncertainties.
Assumptions might include:
Resource availability.
Delivery times of materials or components.
Performance metrics.
Market conditions.
Status in Assumption Log: Upheld vs. Identified
Identified
Meaning: When an assumption is first documented in the log, it is considered "identified." This means the project team recognizes this assumption as a factor that could influence the project's outcome.
Example: An assumption that a key resource will be available throughout the project duration is identified during the planning phase.
Upheld:
Meaning: An assumption is marked as "upheld" when it is confirmed to be accurate or still valid during the project's progression. This status indicates that the assumption holds true and can be relied upon.
Example: If, during the project's execution, the key resource is indeed available as assumed, this assumption is upheld.
Key Points about Assumption Status:
Monitoring: Assumptions need to be regularly reviewed and monitored to ensure they remain valid. Changes in the project environment can impact the validity of assumptions.
Impact on Project: If an assumption is not upheld (i.e., it turns out to be false), it can lead to risks or issues that need to be managed. For example, if the key resource is not available as assumed, it might cause delays or require finding alternative resources.
Documentation: Proper documentation of assumptions and their statuses helps in transparent project management and ensures that stakeholders are aware of potential changes or risks.
By maintaining a detailed Assumption log within the RAID log, project managers can better prepare for uncertainties and manage the project more effectively.
Issues Log
The Issues log tracks and manages current problems that need to be resolved to ensure the project's success. Unlike risks, which are potential future problems, issues are problems that are currently affecting the project.
Key Components of an Issues Log
A well-maintained Issues log includes:
Title: A brief, descriptive title for the issue.
Issue ID: A unique identifier for each issue.
Description: A detailed description of the issue.
Issue Score: The potential impact of the issue on the project (e.g., high, moderate, low).
Impact Description: A detailed explanation of how the issue affects the project.
Owner: The person responsible for managing the issue.
Actions: Steps that need to be taken to resolve the issue.
Status: Indicates whether the issue is open or closed.
Status: Open vs. Closed
Open:
Meaning: An issue is considered "open" if it is currently affecting the project and has not yet been resolved. It requires attention and action to be taken to mitigate its impact.
Example: A software bug discovered during testing that is preventing progress is an open issue.
Closed:
Meaning: An issue is marked as "closed" when it has been resolved and no longer affects the project. The actions taken to address the issue have been completed, and the issue is considered resolved.
Example: The software bug has been fixed, tested, and verified, so the issue is closed.
Actions:
Meaning: The Actions column lists the steps or measures that need to be taken to resolve the issue. It outlines the specific tasks, responsible parties, and deadlines for addressing the issue.
Example: Actions for a software bug might include debugging the code, testing the fix, and deploying the updated software.
Impact Description:
Meaning: The Impact Description column provides a detailed explanation of the issue's effect on the project. It describes the severity and scope of the impact, helping to prioritize the issue and understand its implications.
Example: If the software bug is causing data loss, the impact description might detail the extent of the data affected, potential delays, and the risk of not addressing the issue promptly.
By maintaining a comprehensive Issues log, we can ensure that current problems are identified, assessed, and resolved efficiently, minimizing their impact on the project.
Dependencies Log
The Dependencies log tracks and manages dependencies, which are tasks, activities, or deliverables that rely on the completion of other tasks, activities, or deliverables within or outside the project.
Key Components of a Dependencies Log
A well-maintained Dependencies log includes:
Dependency ID: A unique identifier for each dependency.
Title: A brief, descriptive title for the dependency.
Description: A detailed description of the dependency.
Impact Description: A detailed explanation of how the dependency affects the project.
Owner: The person responsible for managing the dependency.
Priority: The level of priority assigned to the dependency (e.g., high, moderate, low).
Status: Indicates the current state of the dependency
Status: Committed vs. Not Committed
Committed:
Meaning: The dependency has been acknowledged, agreed upon, and committed to by all relevant parties. This indicates a clear understanding and acceptance of the dependency's importance and the necessary actions to ensure its resolution.
Not Committed:
Meaning: The dependency has not yet been acknowledged or agreed upon by all relevant parties. This may indicate uncertainty, disagreement, or lack of clarity regarding the dependency and its implications.
Priority
Meaning: The Priority column indicates the importance of the dependency in relation to the project's timeline and objectives. It helps prioritize which dependencies need more immediate attention.
High: Critical to project success; delays or issues will have a significant impact.
Moderate: Important but not critical; manageable delays or issues.
Low: Minor impact; delays or issues will have minimal impact on the project.
Impact Description
Meaning: The Impact Description column provides a detailed explanation of how the dependency affects the project. It describes the potential consequences of not fulfilling the dependency on time or as expected.
Example: If the dependency is on a software module delivery, the impact description might detail potential project delays, increased costs, or resource reallocations required if the module is not delivered on time.